## Sheet1
Niederman Construction Schedule thru Foundaiton Backfill
Tasks | Start | End
Excavation for Lower Temporary Shoring Prep | Present | 2018-09-10
Temporary Shoring Install | 2018-09-17 | 2018-09-21
Excavation/Lagging at Temporary shoring | 2018-09-24 | 2018-09-28
Foundation Installation | 2018-10-01 | 2018-10-19
Upper Permanent Shoring Wall install | 2018-10-01 | 2018-10-19
Backfill Foundation | 2018-10-22 | 2018-10-26
Excavation/Lagging for Upper Permanent shoring wall | 2018-10-29 | 2018-11-09
Framing Start | 2018-11-12